## Project Tracker
PROJECT PORTFOLIO TRACKER
Active engagements · budget burn · health monitoring · auto-refreshable
ACTIVE PROJECTS |  | AT RISK / OVER |  |  | TOTAL BUDGET |  | BURN RATE
5 |  | 3 |  |  | 890000 |  | 42.19%
ACTIVE PROJECTS
Project | Owner | Start | End | Status | Progress | Budget | Spent | Health
CRM Migration | S. Khan | 2026-01-15 | 2026-04-30 | In Progress | 65% | 80000 | 52000 | Healthy
Power BI Rollout | A. Raza | 2026-02-01 | 2026-05-15 | In Progress | 40% | 35000 | 18500 | Watch
HR System Upgrade | M. Patel | 2026-01-05 | 2026-06-30 | On Track | 30% | 120000 | 38000 | Healthy
Website Redesign | J. Lee | 2026-03-01 | 2026-05-30 | At Risk | 55% | 45000 | 42000 | Watch
Sales Automation | R. Singh | 2026-02-15 | 2026-04-15 | Done | 100% | 28000 | 26500 | Healthy
Compliance Audit | T. Brown | 2026-04-01 | 2026-07-31 | Planned | 10% | 55000 | 2000 | Healthy
Mobile App Beta | A. Khan | 2026-03-15 | 2026-08-30 | In Progress | 25% | 180000 | 45000 | Healthy
Data Warehouse | D. Wong | 2026-01-20 | 2026-09-30 | On Track | 35% | 250000 | 82000 | Healthy
Marketing Site | K. Garcia | 2026-04-15 | 2026-06-15 | Planned | 5% | 32000 | 1500 | Healthy
Customer Portal | L. Mendes | 2026-02-10 | 2026-05-10 | At Risk | 70% | 65000 | 68000 | Over Budget
PORTFOLIO INSIGHTS
Status Summary (auto)
Status | Count
On Track | 2
In Progress | 3
At Risk | 2
Planned | 2
Done | 1